## Лист1
№ | Tasks | Members | S | M | A | R | Time
1 | Discussion, review of information about the project.(100%) | Bazarbayeva Tokzhan | Search out info about project | found resources: 5 | Clearness: 5,feasibility:5 | We need to find out everything about the project | 14/09/20-30/10/20
2 | Software design (UML diagrams)(10%) | Bazarbayeva Tokzhan | Create a diagram for understanding process | performance:5 | Clearness: 5,feasibility:5 | To show how our system work | 01/10/20-11/10/20
3 | Database design | Bazarbayeva Tokzhan | Fill in DB :img, text | performance:5 | Clearness: 5,feasibility:5 | View all DB | 12/10/20-06/12/20
4 | Database, MySQL request | Islamova Gauhar | Make a request to tables | performance:5 | Clearness: 5,feasibility:5 | To know how we quickly adding data into DB | 07/12/20-13/12/20
5 | Databse completion | Islamova Gauhar | Complete all data to tables | performance:5 | Clearness: 5,feasibility:5 | Figure out data in DB | 14/12/20-20/12/20
6 | Realization: Class,Controller, layout | Bazarbayeva Tokzhan | Start to create a bach-end | performance:5 | Clearness: 5,feasibility:5 | To start a back-end code | 21/12/20-27/12/20
7 | Login/Registration form | Bazarbayeva Tokzhan | Create form for access data | performance:5 | Clearness: 5,feasibility:5 | To have access to data | 28/12/20-05/01/21
8 | Admin page: create,add,delete,edit | Bazarbayeva Tokzhan | Create page for admin , CRUD | performance:5 | Clearness: 5,feasibility:5 | To have access and help users | 06/01/21-12/01/21
9 | User page: profile, add comments | Islamova Gauhar | Information about user | performance:5 | Clearness: 5,feasibility:5 | To know data about user | 13/01/21-19/01/21
10 | Sort, search, filter | Bazarbayeva Tokzhan | Create function for convenience | performance:5 | Clearness: 5,feasibility:5 | To easily founding a necessary thing | 20/01/21-26/01/21
11 | Cookie | Islamova Gauhar | Create for time | performance:5 | Clearness: 5,feasibility:5 | To save data of time | 27/01/21-02/02/21
12 | Maps | Islamova Gauhar | Search location | performance:5 | Clearness: 5,feasibility:5 | To know our location | 03/02/21-01/03/21
13 | Front-end : bootstrap | Bazarbayeva Tokzhan | Make the site beautiful | performance:5 | Clearness: 5,feasibility:5 | Show a final front-end of project | 02/03/21-15/03/21
14 | UX analysis | Islamova Gauhar | Make analysis | performance:5 | Clearness: 5,feasibility:5 | To know what experience / impression the user gets from working with your interface | 16/03/21-22/03/21
15 | UI design | Bazarbayeva Tokzhan | Make an interface | performance:5 | Clearness: 5,feasibility:5 | To know the will it be convenient for a person to get his finger on the buttons | 23/03/21-31/03/21
16 | Planning for Testing | Islamova Gauhar | Create a plan for good result | performance:5 | Clearness: 5,feasibility:5 | Manitor the project | 01/04/21-30/04/21
17 | Result: Runing and debugging | Bazarbayeva Tokzhan/ Islamova Gauhar | Show result | performance:5 | Clearness: 5,feasibility:5 | To show our result | 01/05/21-31/05/21